Palestinian National Authority

Palestinian Central Bureau of Statistics

Palestinian Family Survey 2010

Lessons Learned Report

December 2012

This document is prepared in accordance with the standard procedures stated in the Code of Practice for Palestine Official Statistics 2006

© December 2012

All Rights Reserved

Suggested Citation:

The Palestinian Central Bureau of Statistics, 2012. The Palestinian Family Survey 2010, Lessons Learned Report.  Ramallah- Palestine

All correspondence should be directed to

Palestinian Central Bureau of Statistics

P.O. Box 1647 Ramallah, Palestine.

Tel: (972/970) 22982700

Fax: (972/970) 22982710

Toll Free: 1800 300 300

E-mail: diwan@pcbs.gov.ps

Web-site: http://www.pcbs.gov.ps

Preface:

The Palestinian family survey 2010 was carried out under difficult political circumstances that prevailed in the Palestinian territory due to the Palestinian political split and this is reflected in the training process and data collection from the field, where the researchers have been trained on data collection at two different stages in the West Bank and Gaza Strip. The fieldwork in the West Bank started on 3/5/2010 and ended on 12/8/2010 while the fieldwork in Gaza Strip started in September, 2010 till November, 2010.

PCBS supervised all the work stages in West Bank as of training and data collection from the field, while PCBS and UNICEF cooperated together to implement the survey in Gaza Strip by providing field survey’s tools. Questionnaires and other supplies and PCBS pursued all field processes with available means of communications. On the other hand, due to implementing data collection at two different levels, it affected some of the indicators’ calculation in the survey such as: age, education, work and malnutrition indicators as they are to be connected with a period of time and it also affected date of releasing survey data and outputs.

The project’s management tried to fulfill some of the users’ needs   d at    national and international levels and this led to diversity and complexity of the survey subjects and fields.

This report reviews  lessons learned of PCBS experience in implementing this survey, both at the preparatory phase , designing and drafting survey questionnaire, methodology,  field work, data processing and analysis, as well as receiving of  technical missions to review the data.

Contents List

| Subject | Page |
| --- | --- |
| Chapter one: Introduction | 7 |
| - A summary | 7 |
| 1.2 Objectives | 7 |
| 1.3 The Partners | 8 |
| Chapter two: Planning, Organization and Implementation | 9 |
| 2.1 The Planning Phase | 9 |
| 2.2 The preparation phase | 9 |
| 2.3 Defining indicators | 10 |
| 2.4 Questionnaire designing | 11 |
| 2.5 Achievements | 11 |
| 2.6 Training workshops by UNICEF to PCBS team work | 11 |
| Chapter three: Methodology and Quality | 13 |
| 3.1 Methodology | 13 |
| 3.2 Data quality | 15 |
| 3.3 Statistical errors | 16 |
| 3.4 Non-Statistical errors | 16 |
| 3.5 Quality Control procedures | 17 |
| 3.6 Data Evaluation | 17 |
| 3.7 Notes on the sample and sample designing problems | 18 |
| Chapter four: Fieldwork | 19 |
| 4.1 The pilot survey | 19 |
| 4.2 The preparatory phase of fieldwork | 20 |
| 4.3 Data Collocation Phase | 22 |
| 4.4 Special survey tools | 23 |
| 4.5 The problems of fieldwork | 23 |
| Chapter five: Data Processing | 25 |
| 5.1 Data processing phase | 25 |
| 5.2 Daily Progress Reports | 26 |
| 5.3 The procedures of data processing | 27 |
| 5.4 Data entry quality assurances | 27 |
| Chapter six: Lessons Learned and Recommendations | 29 |
| 6.1 Lessons learned | 29 |
| 6.2 Recommendations | 34 |

Chapter One

Introduction

  - Summary about the project

The Palestinian Central Bureau of Statistics (PCBS) implemented the Palestinian family survey 2010  in coordination and cooperation with the Ministry of Health and in a finical and technical partnership with both UNCIEF and  UNFPA to provide detailed and accurate data on family and reproductive health as well as providing indicators on local community health through  measuring of  wide range  indicators on children's death, infants, fertility rates, infertility, spreading of family planning methods, unsatisfied needs,  role of couples in reproductive health and evaluation of  provided services to pregnant women. The survey provided data on early childhood development; children's conduct control, education enrollment, students’ dropout rates, children labor and their rights and protection. In addition to many indicators that monitor children's situation aged less than five years from a healthily point of view, such as vaccines, natural and breastfeeding, spread of malnutrition and anemia. It also provided data on the situation of both youth and elderly. The survey questionnaire included several indicators related to public health like spreading of the chronic diseases, smoking and evaluation of health status of these groups in the society in addition to a big set of indicators that measures social, economical and educational reality for those individuals, their perceptions towards future and assessing their needs.

2.1 Objectives

This survey aims at empowering governmental and national health institutions in obtaining a regular, timely and high quality data which is necessary for implementation, development and monitoring of policies and programs of family and reproductive health in an effective way through the following:

- Updating family and reproductive health database and those related to population, youth and the elderly.

- Monitoring changes on health indicators of the individuals, mothers and children by comparing them with the Palestinian family health data survey of 2006 and other health and demographic surveys.

- Providing a database that can be used by interested researchers to illustrate policies and programs development, including equity in accessing health services and its availability.

- Contributing to evaluating health services programs concerning maternity and child health care.

- Enabling policy decision-makers in various entities in developing future programs and plans based on the results of the survey.

- Providing a set of indicators to measure progress made as well as achieving international and national development goals.

- Contributing in raising awareness in certain issues related to family and reproductive health among individuals in the society.

3.1 The partners

Along with the Palestinian Central Bureau of Statistics, Ministry of Health, UNICEF and UNFPA participated in implementing this survey, where PCBS lead efforts and other related activities of the project as of data collection, data processing, issuing initial results and analytical reports. Other partners contributed in preparatory phase and training of the work team. The Ministry of Health provided qualified laboratory technicians to the field work team.  On the other hand, UNICEF, UNFPA and PNA contributed in financing the project.

Chapter Two

Planning, Organization and Implementation

2.1 The Planning Phase

The planning for implementing this survey began in the first quarter of 2009, as the preparation steps were accelerated at the beginning of 2010. A national advisory committee was formed composed from representatives of  PCBS, Ministry of Health, UNICEF, UNFPA, Jozoor Foundation, WHO, Ministry of Planning and the Ministry of Education to supervise implementing of the project. Moreover, an agreement between PCBS, UNICEF and UNFPA was signed to finance it.

In line with PCBS' policy, producers and users dialogue workshop was held and attended by many of health institutions, research and planning centers in addition to a number of researchers to defining necessary indicators to meet national needs in terms of children health and nutrition. All indicators were included in the questionnaire as of reproductive health, youth and the elderly as well as early childhood development, protection of children and their rights. The questionnaire was modified on the basis of the recommendations in this workshop.

2.2 The preparation phase

Within the context of PCBS and according to projects cycle, there were sets of technical and administrative procedures to be taken into consideration in the preparation phase as of the following:

- A technical committee was formed and assigning of a consultant.

- A national consultative committee was formed including representatives from PCBS, Ministry of Health, UNICEF, UNFPA, UNRWA, Jozoor Foundation, WHO, Ministry of Planning and Ministry of Education.

- The work team began preparing necessary technical and administrative documents to implement the various phases of the project.

- There was a continuous cooperation with partners and donors in terms of technical, financial and administrative matters.

- A timetable was set to implement the survey in cooperation with stakeholders; as different directorates of PCBS developed their plans to implement their tasks during project phases.

- A budget was set with contributions of each donor or partner (UNCIEF, UNFPA and PNA through PCBS).

- Series of meetings were held between PCBS and partners in order to discuss the project implementation, agenda as well as identifying tasks and priorities and other related issues.

- The Ministry of Health provided a staff crew of 12 laboratory technicians to take blood samples and making inspection\examination for eligible children and women at the field.

- A special bid for providing blood test slices was launched and the Ministry of Health provided the survey team with necessary equipment to measure the Hemoglobin percentage in the blood (HB) for both women and children.

- Several contacts were made with medical supplies companies to provide equipment of iodine examination in table salt, but thanks to UNICEF office in Jordan for providing them.

2.3 Defining of Indicators

To come out with a comprehensive general perception on indicators to meet Palestinian society needs, a producers and users dialogue workshop was held by PCBS. In this workshop, participants made their comments on presented indicators that would serve both objectives and local needs.

2.4 Questionnaire designing

MICS4 indicators were considered in designing this questionnaire as it would meet both of national needs and UNFPA indicators. Also, codes of questions were considered to be as the same codes that were adopted at MICS4 questionnaire as well as this was the case in designing the questions and answers codes. The process of designing the questionnaire encountered some difficulties in terms of defining indicators to collect data about and meet partners’ needs; as a result, a main amalgamated questionnaire was formed to meet all needs.

- Main Questionnaire: including the following:

- Household: included demographic and educational characteristics, chronic diseases, smoking, children conduct control (2-14 years old), children labor (5-14 years old), and education of individuals (5-24 years old) and housing conditions.

- Women’s health (15-54 years old) regardless of marital status, including; awareness on AIDS and examination of hemoglobin rate in blood for women (15-49 years old).

- Women who had married at the age of  (15-54 years old) including; general characteristics of eligible qualified woman, child birth and child mortality, maternal care, chronic diseases and ill health due to childbirth, family planning and attitudes towards reproduction.

- Children under five years old including: children health, immunization against child diseases and protection from diseases, early childhood development, malnutrition, examination of hemoglobin rate in blood. It also included on special indicators on child development, rights and protection:

- Attachments Questionnaires:

- Youth questionnaire (15-29 years old) including; general characteristics of youth, awareness of family planning methods and the youth’s perceptions towards family planning, youth’s health status and awareness of sexually transmitted diseases, and finally preparing youth for the reproductive role.

- The Elderly questionnaire (60 years old and over) including; general characteristics of the elderly, social relationships, activities, leisure time, health status of the elderly, and media means.

2.5 Achievements

Within the context of PCBS policy in implementing surveys and implications of its data and the special experience for each survey, this survey results would be applicable through the following:

- A press conference was held to announce the preliminary results of the survey on 9\12\2011.

- The preliminarily results were published on the internet.

- The main findings survey report issued on the internet.

- The survey public data files (PUF) for public use is under processing.

- The preparation of analytical reports and a report on the areas classified as area (C) is under process where contracted researchers are working to prepare these reports and it is expected to be completed and published before the end of 2012.

- The reports on five governorates are under preparation and are expected to be finalized and published before the end of 2012.

2.6 Training workshops by UNICEF to PCBS team

- PCBS participated in a workshop held in Amman on MICS4 on survey methodology, sample and models to be used in the survey where some models were deleted, such as malaria and female circumcision\ Female genital mutilation (FGM.

- PCBS participated in a workshop held in Amman on Palestinian family survey data processing as of computerized data entry and verification program, SPPSS program version 18 and Syntax to be used in data analysis process.

- PCBS participated in a workshop held in Turkey on the dissemination and analysis of  Palestinian family survey MICS4, including the following:

- Strengthening capacity of the participants as well as developing their skills to benefit from data of multiple indicators surveys that implemented in the participating countries, including the Palestinian Territory.

- Empowering participants by acquiring new skills on available mechanisms to be used in data dissemination.

- Increasing participants’ awareness on the most important issues that should be taken into account in data analysis.

- Developing a work plan for data dissemination.

Remarkable moments of the workshop in Turkey:

- Regarding mechanism of preparing the preliminary report, there was a form specially prepared by UNICEF for this purpose, which was similar to the one used by PCBS but without making comparisons or time series to avoiding differences in methodologies between data sources.

- As for the mechanism of preparing the final report, UNICEF recommended a detailed overview of topics that were included in the survey; UNICEF also recommended demonstrating tables within the report texts within chapters and not in annexes.

- With respect to the tables of data quality, UNICEF recommended that the tables should incorporated within the final report as well as tables of sampling errors that should be at the level of each level in which the sample was designed accordingly.

- With regard to educational indicators, UNICEF recommended an age adjustment before extraction of tables to verify accuracy of the ages of children according to the phase.

- Discussions on most prominent proposals made to be considered in analyzing data and preparing the final report, as they were dealing with each included topic in the survey and this would help PCBS in selecting researchers for preparing report chapters. These ideas and proposals would be presented to UNICEF to be used during data analysis.

- Finally, and as for archiving and documentation, a special tool called “micro data management toolkit” was developed and the participants were asked to use it in archiving and documenting the survey. UNICEF was informed that PCBS used to use ADP for documentation and a PCBS would consult our colleagues to review cross cuttings between both programs.

Chapter Three

Methodology and Quality

3.1 Methodology

- Sampling frame:

It was based on sampling frame at PCBS which basically consists of a list of enumeration areas (enumeration area is a geographical area with a number of buildings not less than 120). This frame consists of two parts:

- Sampling frame for West Bank and Gaza Strip: It consists of divided enumeration areas according to the general census of 2007. In West Bank, each enumeration area contains a list of households that inhabit every housing unit along with the necessary background identification of each household; whereas, in Gaza Strip, each enumeration area contains lists of housing units with their addresses which would make contacting and accessing to these household easier.

- Sampling frame for Jerusalem (J1): It consists of divided geographical enumeration areas with a number of housing units within each enumeration area without having details about households. It also can be benefited from the existence of enumeration area borders, households and individuals numbers within each area, without being able to identify the households’ addresses or housing units.

- Strata of sampling design

In this survey, two variables were selected to divide the society into strata depending on homogeneity of the society. Previous studies showed that the Palestinian households can be divided into homogeneous groups as follows:

- Governorates: there are 16 governorates in the Palestinian territory; 11 governorates in the West Bank and 5 in Gaza Strip.

- Locality type:  localities were divided in every governorate to: (urban, rural and refugee camps.)

The main indicator was approved in estimating the sample size (r), which is (a midget or unusually short stature) indicator for children under five years old. In the last MICS3 survey in 2006, it amounted to 10.2% and in reference to the general census data of 2007, the percentage of children (0-4 years old) (p) is 14.1%. Thus, the final calculated sample size = 15,355 households.

- Designing of sample and type:

After determining the sample size of 15,355 households, a probability sample was selected: where a multi- stratified cluster sample was selected as follows:

- First phase: the selection of a clusters sample (enumeration areas) by an PPS   (probability sample which is a proportional to sample size) without return, where 644 enumeration areas of the overall framework were selected.

- Second phase: the selection of 24 households from each selected enumeration area in the first phase. These households were chosen in a systematic manner. All targeted individuals from the following groups were classified: women aged (15-54 years old), the elderly, and children aged (0-5 years old).

- Third phase: the selection of individuals from the group of 2-14 years old (for a set of questions), where an individual from the group of 15-29 were selected by using random kish tables.

- Response rates:

Response rate of households in the Palestinian territory amounted to 89.4%, while 93.2% in West Bank and 87.5% in Gaza Strip. On the other hand, response rate ranged between 80.0%- 99% according to the targeted group in the sample.

- The methodology of hemoglobin examination rate in blood:

An examination of hemoglobin rate in blood for women aged 15-49 years and children aged 6-59 months were done by qualified nurses within the fieldwork team.

- The methodology of iodine examination rate in table salt

Field workers were trained to check out the iodine in table salt by taking a full teaspoon sample of the table salt that was used by the household the previous night (at the time of the survey) and adding a drop of the liquid (iodine examination material) to table salt.

- Weights calculation  of households

First:  households weigh calculation

- In the first phase: enumeration areas weight was calculated depending on the probability selection of each enumeration area (PPS).

- In the second phase: household weight was selected from each enumeration area.

- Then, we calculated the initial weight through multiplying the weight of the first phase with the weight of the second phase to get the initial households’ weight.

- Households’  weights were modified according to responses so that the modification is to be calculated as follows:

Processing the non-response cases by modifying the weights:

As the:

wi: the initial weight before the modification of household i.

g: modification category according to the governorate and locality type.

fg: weight modification modulus according to category g.

∑ ng wi: weights' sums in category g.

Σ∘.cg wi: sum of increasing weights of coverage cases.

Σrg wi: sum of weights of response cases '.

To obtain the sum of “ fg” for each category and by the end, we would  get the modified household weight according to response (w'i) by using the following equation:

- Those weights should be modified depending on households  estimations by mid of 2010, and the modified category would be the stratum (governorate, locality type) and thus, we would get the final households weight.

- After that, we examine weights by comparing the total weights of with households’ estimation.

Second: individuals' calculation weights

- By amalgamating of the households’ weights to the total individuals' file so the individual's weight is as same as the household’s weight if all the individuals from a required group were selected; however, if an individual from the household was selected, his weight would be as the household’s weight multiplied by the individuals' numbers from the required group.

- Then, by modifying the individuals' weights depending on the population estimation of mid 2010 based on the modification group: region (West Bank, Gaza Strip), gender (male, female) and age group and then one gets the final individuals’ estimation in the required group.

- Finally, by examining the weights by reviewing the total weights with the same total in the individuals’ estimation in the required group.

  - Data quality

The concept of data quality consists of multiple aspects, starting from planning for implementing a survey and ending up with publishing, disseminating understanding and benefiting from data.  The most important components of the statistical quality include: accuracy, comparability and quality control procedures.

To ensure a high quality data, a series of steps should be followed:

- Examining and reviewing survey tools.

- Conducting training to fieldworkers on questionnaires in accordance to international recommendations by qualified instructors for a sufficient period of time.

- A constant supervision for all phases of field work in all areas.

- A field and office auditing on the filled questionnaires.

- A continuous examination for data entry process in terms of consistency and sense.

- During the field work, 16 fieldwork examination tables were used to examining distribution and re-gathering of questionnaires based on discrepancy, sex rates, age heaping, targeted groups and other related examinations.

The data accuracy examination includes multiple aspects of the survey including; mainly statistical errors due to using the sample as well as non- statistical errors due to work team and survey tools, response rates and its impact on the estimations.

3.3 Statistical errors

The data of this survey is affected by the statistical errors due to the use of the sample and not the comprehensive survey of all community units where differences from expected real values would certainly appear, Variation was calculated for the most important survey indicators.

The variation calculation table at the Palestinian territory'' level for a selected indicators

| Variable | Rate of estimation % | Standard errors % | Coefficient of variation % | Confidence interval 95% |  | No. of Observations |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Minimum % | Maximum % |  |
| Percentage of women aged (15-49 years) who currently using any of the family planning methods (at the time of the survey) | 0.5254 | .00528 | .0110 | 0.515 | 0.536 | 10,617 |
| Percentage of women aged (15-49 years) who received health care during their pregnancy of the last birth delivery(at least once by skilled personnel) during the two preceding years of the survey | 0.984 | 0.00254 | 0.003 | 0.975 | 0.985 | 4,471 |
| Birth deliveries percentage (last birth delivery) that took place in health institutions during the two preceding years of the survey | 0.9860 | 0.00339 | 0.004 | 0.973 | 0.987 | 4,471 |
| Percentage of women who had given birth during the two preceding years of the survey by a cesarean birth delivery | 0.1671 | 0.00588 | 0.035 | 0.155 | 0.179 | 4,471 |
| Exclusive breastfeeding under 6 months | 0.265 | 0.01269 | 0.044 | 0.263 | 0.314 | 747 |
| Underweight prevalence | 0.032 | 0.00226 | 0.061 | 0.033 | 0.042 | 9,158 |
| Stunting prevalence | 0.1093 | 0.00402 | 0.037 | 0.101 | 0.117 | 8,964 |

3.4 Non-Statistical errors

Several procedures were taken to reduce impact of non-statistical errors, so highly qualified field workers were selected to training them on fieldwork techniques of filling questionnaires as well as providing them with a field manual that pertains special key to the questions of the questionnaire and its filling techniques and techniques of dealing with respondents in order to reduce the rejection rates and giving correct and unbiased answers.

As for desk work, a special team was trained to audit the questionnaires and to explore field errors to reduce fieldwork errors rate as well as reducing the errors rate which might occur during data entry. A very accurate data entry program was designed to avoid any systematic errors during data entry process.

The field workers’ reports indicated that interviewees encountered difficulties in understanding some of the questions and terminologies; however, and as a result of qualified fieldworkers, they managed to overcome those problems. Generally speaking, the interviewees’ acceptance of the questionnaire was good.

Sources of non-statistical errors could be summarized as follows:

- Errors resulted from the questions asked by the field workers.

- Errors resulted from the interviewees’ understanding to the question and as answers were based on such understanding.

3.5 Quality Control procedures

Several procedures were taken to ensure data quality, where the field works got trained on techniques of filling questionnaires in the field, in addition to conducting field visits to the field workers to ensure a safe data collection. On the other hand, the questionnaires were audited before being posted to data entry. A special data entry program was designed with rules to avoid any errors. After that, data entry was examined to ensure being free of previous errors. After receiving of the raw data file,   data verification and examination of the outliers, consistency between different questions in the survey were done.

3.6 Data Evaluation

There were different methods taken to evaluate the data including:

Frequencies of missing values, answers  of "other" and "I don't know", examination of inconsistencies between different indicators, data internal consistency examination and comparing  data with previous surveys and other sources. The results of such examinations showed that data quality and consistency was high. The comparison between the results of the report and the results of previous surveys 2000, 2006 showed that it's logical and homogeneity in the results.

PCBS received a technical mission as dispatched by ESCWA and implemented by Dr. Marwan Khawaja to review data on fertility and mortality and concluded that data was of a high quality and that the differences in values of indicators between PCBS and UNICEF was  due to the time reference  in calculations of these indicators, as both mechanisms could be used. UNICEF dispatched another technical mission to PCBS to evaluate the data s during the period between 16/7/2012-20/7/2012 as the mission objectives and conclusions will be detailed in chapter six.

3.7 A review on the survey sample and the accompanied problems during the sampling design

The sampling design and the selection of sample methods were considered one of the most important things that affect accuracy of the survey indicators estimations so it should be addressed before the implementation of the survey. In the current survey, a sample was designed to be representative for all the society; however, there was a difficulty in reaching some of the enumeration areas in Jerusalem and Ramallah, where Jerusalem governorate; especially, in the old city, Israeli occupation measures and obstacles were enormous in interviewing and approaching households over there.

Among other things that affect accuracy of the indicators estimation was the non- response problem; where in this survey, the non- response percentage was within the expected, where it reached at the Palestinian territory level about 10.6%. of which 6.8% in West Bank and 12.5 % in Gaza Strip. As the highest non- response percentage was in rural areas amounted to13.9%, followed by urban areas at 13.7% and refugee camps by 7.9%.

By comparing with the non-response percentage in the health survey of 2000, this percentage amounted to 6.0% in Palestinian territory (7.0% in West Bank and 5.0% in Gaza Strip). In 2006, it amounted to 15% in Palestinian territory (18% in the West Bank and 11% in Gaza Strip). Even though of the non- response percentage, the children and women sample size was not affected because the sampling design took into account the non-response percentage by adding 15% to the sample.

It is noted that the Palestinian family survey covers MICS4 survey in addition to a range of modules and this sampling design affected standards of  MICS4 survey; especially, in weights calculation. Weights calculation models for the indicated groups (woman, child and family in general) in MICS4 survey were available at UNICEF whereas the other groups (elderly and youth) were separately dealt with in weights calculation. With the fact that the sample's design took into consideration that the main indicators were that of  MICS4 survey indicators, so it was recommended to separate MICS survey from any other modules in order to be dealt with in a standard way and without any other problematic issues because of other modules.

Chapter Four

Fieldwork

  - The pilot survey

- Objectives of the pilot survey

The pilot survey is considered an essential part of the preparatory phase for any survey. It is a mini-survey and through it, one could examine all of the procedures and any needed steps to ensure the success of the main survey. The pilot survey was carried out to test several issues such as:

- Achievements rate and required work team for the main survey.

- Fieldwork mechanism.

- Financial and human needs assessments.

- Examining the questionnaire and the survey tools of weights and length scales.

- Accessing and approaching households addresses.

- Time reference and the ability to calculate ages appropriately to obtain accurate data.

- Examination of the training program in terms of duration, training techniques and mechanism, the ability of trainers to deliver the information and using training materials.

- Examination of desk and automatic auditing mechanisms.

- Survey frame and qualified individual.

- Data entry program.

- Distribution of the pilot survey sample:

The pilot survey sample size was estimated at 144 households for examining methodology, questionnaire, achievement and all the survey tools. Where the two governorates of (Ramallah and Al-Bireh governorate and Hebron governorate)) in the West Bank were chosen as sample for the pilot survey and each governorate was divided according to locality type (urban, rural, and camp)

- The pilot survey training:

A training course was held for the pilot survey work team for 9 days from 7/2/2010 until 16/2/2010 as well as a special training for the supervisors and auditors. During the training course, the team was trained on terminologies and concepts of the survey, techniques of filling the questionnaire, asking questions, methods of measuring height and weights for children, salt examination methods, training nurses on how to examine blood. Moreover, they were trained them on techniques of conducting an interview and a briefing on fieldwork tasks, accessing mechanism to selected families in the sample. The training also included lectures and practical training at office and fieldwork exercises.

- The implementation of the pilot survey in the field:

Two governorates in the West Bank (Ramallah and Al-Bireh governorate and Hebron governorate) were selected to implement the pilot survey. The work in Ramallah governorate started on 22/2/2010 and ended by 4/3/2010 whereas in Hebron governorate, it started on 23/2/2010 and lasted for six days. 13 trainees worked on mechanism of filling the main questionnaires, including youth and elderly and other two male trainees were trained to fill in the youth questionnaire.

At the end of the pilot survey, an evaluation was made, in addition to problems and work techniques were discussed during a meeting with the team. The recommendations were summarized and the necessary modifications were taken into consideration based on the evaluation results.

In the light of the pilot survey results, it revealed that the daily achievement rate for the fieldworker was as follows:

- The main questionnaire (55 pages), including both the elderly and the youth questionnaires (females): 3 questionnaires.

- Youth questionnaires (males): 6 questionnaires.

The interview period average for the questionnaire with all multiple parts, ranged between two to two hours and a half.

4.2 The preparatory phase of the fieldwork

Series of procedures were followed to implement the activities within the time schedule as follows:

- An action plan and a budget for the fieldwork and a timetable were set to determine necessary project requirements in terms of supplies and required tools for the fieldwork team (weighing machines and height measurement scales, blood testing devices and salt testing materials).

- The identification of required work team in each governorate according to the sample size, composition of field work team, mechanisms of work and the administrative responsibilities of the work team.

- The preparation of the budget of the fieldwork in coordination with project management and finance department of PCBS.

- Providing a staff for the project through vacant Jobs advertisements; especially, for girls. Then, the committee made interviews for all the applicants and selected the highest marks with a former experience with PCBS.

- Team Work selection and the determining of team structure for main work:

110 employees worked in the survey in West Bank and they were distributed on 13 groups according to estimated achievement average of (2.5-3) questionnaires, work period and sample size in each governorate. In this regard, the team consisted of a supervisor, an auditor, 3-5 data collectors, an assistant to do weights and height measurement, in addition to a laboratory technician to make blood test for the qualified individuals. On the other hand, 15 male field workers worked in order to fulfill the youth questionnaire (males).

- Training of fieldwork team in West Bank:

In the light of  the evaluation process of the pilot survey, adoption of its recommendations related to the questionnaire, the work mechanism, the team structure, the training program and the needed staff , preparation for the training course to the main survey team work was initiated,

As for other issues related to the training, it included a comprehensive explanation for the various parts of the survey: family, women and children questionnaires. Also, they were trained on the concepts of all the related parts and data filling mechanisms, in addition to the training on the youth and elderly questionnaires, the theoretical and practical use of the weights and height measurements of children, and salt and blood test mechanism.

At the end of the session, an exam for the female trainees was held to assist them based on certain classification standards as follows: daily evaluation at 40%, and the final exam at 60%. In this regard, the supervisors, auditors, assistants, and the interviewers who got the highest marks were selected. After that, a workshop was held for them for a period of three days included  team tasks, supervision, follow up mechanism, revision, in addition to auditing rules, work control methods, solving  field  problems and filling the field work control forms.

On the other hand, the female field workers were selected on the basis of the academic qualification and efficiency and they were trained theoretically and practically on the questionnaires, models and maps for 14 days from 30/3/2010 till 14/4/2010.

- Training of the fieldwork team in Gaza Strip

Due to the Israeli imposed movement restrictions on movement to Gaza Strip during survey implementation, PCBS took several procedures as follows:

- The project management trained the UNICEF team in West Bank and in turn, the UNICEF team took the role of training in Gaza Strip.

- The training of the trainees in Gaza Strip on the questionnaire via the video-conference.

- Mr. Pierre, UNICEF advisor went to Gaza Strip to train the female fieldworkers over there.

  - Data Collocation Phase

- Fieldwork  period:

The fieldwork in West Bank governorates began on 3/5/2010 till 12/8/2010 while the fieldwork in Gaza Strip governorates began on September, 2010 till November, 2010.

- The field visits in the West Bank:

The process of data collection witnessed several field visits of project manager and technical committee members based on a prepared visits schedule, in addition to the field work coordinators’ visits for the governorates to follow up data quality and accuracy as well as the female field workers’ commitment to the instructions. The female assistant helped in the weights and height measurement process and the follow ups of the laboratories technicians by taking blood samples from the qualified individuals among children and women, in addition to follow ups visits to the absentees and non-respondents to persuade them to cope with field workers.

- The field visits in Gaza Strip

The fieldwork was followed up by a trained employee on the video conference since there wasn't any presence for PCBS staff and the inquiries were answered via phone and emails.

- Follow ups means:

- Work control models:

Special survey forms were prepared to adjust the daily achievement and the delivery process of the questionnaires between the coordinator, supervisor, and the supervisor, field worker and the auditor on the other hand. The supervisor's role was to prepare a daily progress report including the completed and non- completed questionnaires as well as the rejection for each team in order to be submitted to the coordinator.

- Follow-ups on Telephone:

The field workers could communicate with the fieldwork coordinator or with the department director via phone in cases of encountering any difficulties or problems in the field in terms of technical inquiries related to the questionnaire or special field work consultations.

- Circulations:

Several circulations were issued aiming at guiding field workers and solving some technical problems of the data collection. On the other hand, the circulations were copied to data processers to incorporate any modifications or developments on the instructions.

- Special procedures on  data collection phase:

- At the beginning of the fieldwork, there was a disconnection in the work due to the lack of a sufficient number of printed questionnaires as well as the delivery of the iodine examination materials and blood test slices were delayed and then field work was resumed after the completion of the printed questionnaires.

- All field work teams in different governorates were pursued through various means of communication and field visits.

- There was no presence for PCBS staff in Gaza Strip, so any inquiries were answered via phone and emails.

  - Special survey tools and means

- Height and weight measurement scales:

During this survey, several measurement scales that were used in several countries such as: a modern weight scale, in addition to height measurement tool which is consisted of two pieces of wood fixed with a length scale. The team did great efforts in the field; however, they encountered a number of problems during their mission:

- Some children refused to take off their shoes during the measurement process.

- Some children refused to stand up on neither the weighing scale nor the height measuring meter.

- There was a difficulty in carrying the height measuring meter from place to another.

In this context, it is worth mentioning that the used weighing scale and height measuring meter in this survey were the same tools that have been used in the Palestinian family health survey 2006.

- Blood test device:

A new modern device was used to examine the hemoglobin in blood, the prominent features of this device is to give an immediate and accurate result of the examination. Several technical procedures were followed to ensure the quality of the results as follows:

- The laboratory technician was asked to make a daily checks.

- A random sample of hemoglobin examination was taken from the tested individuals by using the same device and another examination to be done in order to ensure results accuracy.

As for the respondents' attitude towards blood test, it was highly expected in some cases such as the rejection of qualified woman to have the blood examination for herself and her children.

4.5 The problems of fieldwork

1. The delay in submitting the blood slices, salt examination materials and the printed questionnaires caused an interruption in the work.

2. The drop outs from the team work in middle region and Jerusalem team led to a delay in accomplishing the tasks in comparison with other governorates.

3. The inaccuracies in some of the blood devices and the unavailability of an alternative to it.

4. The insufficient teamwork on the youth questionnaires in some areas, especially in the middle region.

5. The unavailability of targeted families in their houses, especially in the middle region.

6. The fieldwork problems in Gaza Strip were solved via phone and emails and there wasn't any follow ups on the field by the project management.

- Non- statistical errors that emerged during data collection:

- Several procedures have been taken to reduce the impact of the non-statistical errors.  Qualified fieldworkers were selected to train them on the fieldwork techniques , techniques of filling questionnaires, in addition to provide them with a booklet manual which contains special key for the questionnaire questions and its filling techniques as well as dealing with the respondents to ensure  less rejection rates and giving truthful answers.

- An accurate data entry program was designed to reduce errors rate which may occur during the data entry process.

- The field workers reports showed that respondents encountered in some cases difficulties in understanding the questions and terminologies; however, the qualified field workers were able to overcome those problems.

Finally, one could summarize some resources of the non-statistical errors that appeared during the implementation of this survey as follows:

- There were some errors resulted from methods of  asking questions by the field workers due to the large number of questions in the questionnaire and the large number of the targeted group in the survey. Thus, the respondents encountered difficulty in understanding the questions.

- Some children refused to take off their shoes during the measurement process.

- Some children refused to stand neither on the weighing scale nor on the height measuring meter as they were frightened of the wood piece to be put on their heads; as a result, the measurement process took a long time.

- The weighing scale broke down in some of hot areas.

- Some children resisted the needle’s process.

- In some cases, the qualified woman refused to make blood test for herself and for her children.

Chapter Five

Data Processing

  - Data processing phase

The data processing phase went through several sub-phases starting from the preparation phase and ending with the completion of public use data file completion and these sub-phases were as follows:

- The Programming: during this phase, data entry program were prepared by using CSPRO package and all modifications were reflected in the preparation phase or during the training on the questionnaire. Modifications on data entry screens, and the work on reversing automated rules and the verification of the data entry program, in addition to designing a program that reflects all automated and offices auditing of data verification rules, as well as examining outliers after completion of data entry and auditing of any enumeration area to ensure data quality.

- Questionnaires delivery and controlling phase: during this phase, data entry supervisor receives the questionnaires from fieldwork coordinator through a well-prepared form that contains details on the questionnaires according to the enumeration area including; the main questionnaire, women, children, elderly and youth. Where the employee ensures a well receipt of all questionnaires in addition to signing a receipt form stating accurate date.

- The data entry and training phase: data entry and training phase includes  three processes as follows:

- Five data entry workers did an exercise of processing data of some correct and incorrect questionnaires to ensure the program effectiveness in all necessary actions. Then, deleting of such data files during this training process.

- Data entry workers according to deliveries of the questionnaires where the data entry workers were trained for two days and then deleting such training files to start a real data processing.

- Providing a staff of four specialized researchers to solve any problems they may encounter during this data entry process.

- Data Entry Phase: this phase started on 17/6/2010 till 12/2010 after receiving the questionnaires from Gaza. The data entry staff consisted of 30 temporary workers and their output average was 15 questionnaires per day. On the other hand, three data auditors were provided in the data entry hall to solve any technical problems according to previously prepared instructions , manuals and previous  training of the field work team to ensure consistency, understanding and coherency between the questions to be able to take decisions at the office or to return back the questionnaire again to the field to modify it by the field worker either by re-visiting the families or by contacting them on phone.

- Data auditing phase: during this phase, the data auditor compares the entered data with original questionnaire and modifying any errors according to the followed procedures through a prepared form for this phase and then preparing a daily progress report and data accuracy for project management for their follow ups. In this regard, data auditing was done in data entry  offices at a rate of 60%

- Data Verification: An automated data verification rules were developed among questions at the questionnaire level to examining consistency of the questions with each others. Then, the auditors’ team reviewed and modified the questionnaires errors based on instructions or returning back the questionnaire to the field. The data verification program implemented for each enumeration area, a report should be printed and then all the questionnaires with errors should be audited in order to examine any related variable and modifying it in data entry program. After this process, we got out a second report for the same enumeration area to ensure that all questionnaires were modified correctly. Other reports were to be sent to project management after auditing the data to modify the questionnaires accordingly. Correct questionnaires were documented to avoid any duplication in auditing; however, these examinations weren’t comprehensive, especially in regard to the consistency among questions and different parts of the questionnaire.

- Receipt phase of questionnaires: in this last phase, all questionnaires were classified according to locality type and enumeration area and then were registered in specialized and approved forms. Finally, they were being sent for archiving within special boxes in the stores. The survey was completed on 18/1/2011.

- Mechanism of dealing with returned questionnaires: in case of an error, the auditor checks the error and after confirming that it isn’t an error in the question value, accordingly:

- The modification of the question error and any related questions to proceed in data entry of the questionnaire.

- The returning back of any questionnaire to the field to enter a value (not defined) to have data entry process completed of the questionnaire, and the returning of any questionnaire to the field should be only for one time to solve all errors.

  - Daily Progress Reports:

To keep in touch with the project management and fieldwork management, daily progress reports were prepared to describe data processing phase and this could be done according to the following mechanism:

- The daily report: it contains the date and number of received questionnaire daily. Also, it includes accumulative number of the questionnaires, the total number of the entered questionnaires, and differences between the entered and received questionnaires to track the percentage of the data entry, received questionnaires, audited, and the returned questionnaires to the field.

- The daily report also includes the governorates’ names and numbers of received questionnaires from each governorate within special form for controlling purposes on the flow of the questionnaires.

- The sample is uploaded at the governorate level to be compared with the achievement percentage.

- The report is sent to the project manager every morning to review the progress on the project and data entry process and notes given by data entry department. The project manager coordinates with data entry department to clarify any inquiries or modifications.

- Two copies of the daily report are prepared; one copy is delivered to the project manager and the other to data processing department.

  - Pursued  procedures in data processing

To abide with the special item on data processing within the survey plan, several procedures were taken in preparing and implementing the project:

- Preparing of needed supplies before the survey to avoid interpreting data entry process.

- Preparing and distributing of instructions on data entry program before launching this process.

- Entering incorrect questionnaires to the program before data entry process to validating and examining the data entry program.

- Auditing of all received questionnaires from the fieldwork office by the data entry supervisors against signing of special receipt forms.

5.4 Ensuring quality of data entry

Several procedures were taken to ensure quality of data as follows:

- Data entry team was trained on data entry program, and the program was examined by trial questionnaires before the arrival of real questionnaires.

- All automated data auditing examination and data verifications programs were uploaded to ensure data quality.

- The data are delivered every week or two weeks for the survey management to be examined along with a report on errors statements to be circulated to data entry department to be corrected.

- Data entry rules were set in a way to ensure data entry and revealing any errors in time, where the transitions between questions were set and to ensure  allowed range for each question  to be entered as well as to make sure that the questions that contain a percentage does not exceed more than 100%; however, all the examinations were not taken into consideration, especially the consistency examination between the questions and the different parts of the questionnaires and this led to dropping a number of questionnaires in the data verification phase.

Chapter Six

Lessons Learned and Recommendations

6.1 Lessons learned from the project

First: The Preparatory phase:

During this phase, a workshop was conducted in Amman on designing of MICS 4 with a focus on the following issues:

1. MICS4 team informed PCBS of their will of implementing MICS4 as a in adjustable single package especially to methodology, the sample, the data entry program, order of questions and templates in the questionnaire, and the uses of approved symbols by UNICEF to facilitate of extracting tables and information as it is previously agreed upon.

2. UNICEF gave up using of unnecessary models in Occupied Palestinian territory like the model on Malaria, female circumcision and others. UNICEF pointed out that what does not apply on a country, it is unnecessary to be adopted on the condition that the package of MICS4 should be implemented as one single package.

3. UNICEF did not oppose the idea of including additional questions or models to the questionnaire on the condition that they should not stand inconsistent with uses of approved symbols of questions by UNICEF and the order of questions and models in accordance  with MICS4.

4. UNICEF did not oppose the idea of ​​using any title for the survey which to be implemented by PCBS in 2010, whether as a family health survey or as MICS project. UNICEF explained that what is important is the methodology that will be adopted by PCBS, whether to follow the methodology as of MICS or is it a national project that uses only MICS indicators and not MICS package.

5. UNICEF pointed out that the non-use of MICS4 methodology will affect the technical support to be provided to PCBS, where the technical and financial support would be provided by UNICEF to PCBS as a partner only and according to what is being agreed upon. While, in the case of adopting MICS methodology, the technical support will be provided as an essential partner including technical training courses and workshops to be conducted by the working group of MICS.

6. PCBS affirmed that they are willing to join the list of countries that will implement MICS4 and the needed support would be for a national survey with MICS methodology.

By launching of the survey activities with conducting a pilot survey, it was accompanied by some kind of lack of clarity such as determining a title of the survey, questionnaire and data entry designing programs. Perhaps, these conditions led to a delaying in implementing the pilot survey as originally scheduled, which affected the rest of project activities, and thus modifying the timetable of main survey and other project activities. Where UNICEF, at first, did not oppose the idea of ​​using any name for the survey, and at the beginning of conducting the pilot survey, UNICEF and UNFPA discussed the project title for long time. Therefore, it was inevitable from the very beginning to identify these issues and to agree upon them before launching the project to avoiding any to confusion among survey management and distressing other activities of the survey.

Second: Preparing of the questionnaire and training booklet.

In this phase, the questionnaire was prepared on the basis of MICS4 indicators. As well as, it included a set of indicators that meet the national needs and another set that fulfill the needs of UNFPA. In addition to two modules were added on the questionnaire as of the youth and the elderly questionnaires. The codes of questions were as the same codes adopted in the questionnaire of MICS4, in addition to rephrasing the questions and the answers codes.

The phase of questionnaire designing went through hard times concerning agreement with (UNICEF) upon the questionnaire and its indicators or even the layout of the form, and this took a lot of time until it ended up in 28/3/2010 as UNICEF head quarters in New York   commented on the questionnaire with some observations and those had been worked out in accordance with our national needs. The work was finalized on version (2.1) after PCBS had finalized preparations for field work. It is worth mentioning that PCBS incorporated necessary modifications and comments on all versions inconsistency with the reality of Palestinian community and national needs.

Those changes (amendments) and additions increased the size of the questionnaire. This was one of the important reasons that led to the postponement of the implementation of the pilot survey, which doubled the burdens on field workers and prolonged time consumed in interviewing families. Hence, we should think of another mechanism for implementing the survey to alleviate the questionnaire and subsequently easing burdens on field workers and families to securing high data quality. As a result, it is possible to reconsider one of the following options:

- Abiding to MICS questionnaire and requirements of the survey according to UNICEF.

- If there was no  other options but implementing the survey to meeting  the national  and UNFPA needs concerning the addition of modules to  the survey on  the youth and  the elderly questionnaires, one should consider the following:

- Re-considering mechanisms of forming the team work in terms of numbers and the technical skills.

- Concrete coordination and arrangement of workshops to be conducted by UNICEF to the project management so that all requirements of PCBS partners are considered and avoiding confusion that might occur during implementation of the survey and securing enough time to fully implement project requirements.

Third: The training phase.

- At this phase, the training was conducted in West Bank and Gaza Strip at different times because of prevailing political conditions in the Palestinian territory due to the Palestinian split. As some indicators were assigning to a time reference, this led to confusing with the project management in matters of age, education, work and indicators of malnutrition. Therefore, it is necessary to assign indicators to the interview time and not to a specific date as time reference.

- UNICEF in cooperation between PCBS implemented training in Gaza Strip where the project management oversees any inquiries received from Gaza Strip during the training time over phone or by emails; however, there was no direct training and this might affect the training effectiveness.

Fourth: The field work phase

- The field work was not launched immediately after the training due to discussion with UNICEF concerning their observations on the questionnaire and also a failure in providing necessary equipment and materials for salt examinations and shortages of blood test slides in Palestine as well as implementing this survey in Gaza Strip.

- The field work in West Bank took longer time than scheduled due to starting field work without having necessary equipment and materials for salt examinations and blood test slides as well as not having an enough number of printed questionnaires, as such shortages were met in a month when UNICEF and UNFPA met their obligations in providing blood test slides, materials of examining salt, and printing the rest of the questionnaires.

- The field work in West Bank was launched on 3/05/2012 and continued up to 12/08/2012; meanwhile, the field work in Gaza Strip started on  9/2012 till 11/2012 but the rest of filled questionnaires didn’t reach the data entry hall until 12/2012. Therefore, the beginning the field works in different times in the West Bank and Gaza Strip led to confusion in calculating of some indicators like those of education, work, age and malnutrition   because of their linkage to a time reference period. This matter was one of technical issues that weren’t considered although MICS methodology pointed clearly at the necessity of calculating ages in accordance to the date of interview and not to a reference date. This led to a delay in verifying the data which affected finalizing all outcomes of the survey with long delays.

- Lack of accuracy in some blood test slides and the lack of alternatives led to a non-compliance in filling the questionnaire at once, so it is supposed to examine these blood devices well before using.

Fifth: Processing data and data entry program

- In this phase, PCBS participated in a workshop about data processing of the survey on 9-5-2010 in Amman. UNICEF conducted a workshop after five days of launching of the field work.

- The readiness of the data entering program that was prepared by PCBS before the workshop, and taking note that progress was going satisfactorily on the survey and faster than UNICEF planned, so the project management and the authorized PCBS department started in programming the questionnaire and preparing data entry program in according to the project life cycle without coordination with UNICEF due to high PCBS experience. We would like to assure that the designing of data entry program did not take into account the standards set by UNICEF. This eventually led to a gap between PCBS and UNICEF about the program and its components, data entry mechanism, testing and linking it. Perhaps, the timing of designing the program before participating in the workshop held by UNICEF for this purpose, led to widening the gap in terms of PCBS commitment in required standards and not examining the program by UNICEF in early phases of the survey. This shows imbalances in communications between PCBS and UNICEF and lack of patience in making right decisions within PCBS, not to mention the lack of bearing responsibility as required.

- Refusal of PCBS prepared data entry program as it should meet UNICEF standards.

- There was not available time to prepare a new data entry program to match with UNICEF standards due to big size of the questionnaire.

- There was a decision by PCBS depending on its designed program of data entry due and by virtue of PCBS experience in this area. Besides, the program took into account UNICEF requirements in terms of files order and their requirements.

- Up on finishing data processing at PCBS, the files were dispatched to UNICEF and there was a long debate between PCBS and UNICEF because the data files didn't match with their requirements as PCBS didn't use that program designed by UNICEF and as PCBS did not comply with data entry standards led to lack of sufficient examinations on data entry program and so not implementing of many of tests that did not originally exist at all.

To put an end for the dispute between PCBS and UNICEF regarding data files, several measures were taken including the following:

- Several meetings were held with Mr. Rashad, a representative from UNICEF to handle these issues of the data files

- There was a role for UNICEF in testing and verifying the data in an advanced phase.

- There were agreements on several dates to deliver the files to PCBS, but that didn't happen.

- PCBS team participated in the workshop in Turkey where it was supposed that PCBS team will receive the data files permanently from UNICEF, but that didn't happen.

- When the files were delivered by UNICEF to PCBS on 14/09/2011, they were checked by PCBS as there were comments on incomplete cases, and notes about the mechanism of merging the ladies files. It was found that Mr. Rashad was working on an old copy of the files that was dispatched to him previously, and he did not work on updated version that was sent to later.

- The confusion that happened was corrected in addition to discussing important issues including women and enumeration areas which we couldn't collect data from due to political reasons

- There was another discussion between PCBS and UNICEF about the weights being used and that took a long time too.

- Because of the long period that UNICEF' took in reviewing the data files and the  problems encountered by the preparation of the files within UNICEF criteria, PCBS was forced to announce the results of the survey during a workshop and working on the outcomes of the survey by  available files at PCBS.

- Mr. Rashad’s way in dealing with the survey files led to confusion and delays, and these were obviously noticed through contradictions in his requests and that moving from one point to another without a radical solution to the fundamental issue, namely the preparation of data files in their correct form according to UNICEF request.

- Preparing final files took a long time, and thus affected the outcomes of the survey and caused delays in the time schedule.

- In a subsequent period, a technical mission dispatched by UNICEF to PCBS for one week from 16/07/2012, aiming at reviewing the data files at PCBS and their consistency and conformity with standards of MICS4 and to get out with final data files, It was agreed to adopt the final data files from UNICEF and PCBS on 08/08/2012.

Sixth: Data Analysis

- Due to long discussion with UNICEF on data files and their consistency with MICS4 standards, data analysis and extraction of indicators were delayed. In this regard, it was based on the indicated files at PCBS along with the Syntax files from UNICEF in data analysis and extracting tables as well as extracting of tables that meet national needs. The initial results and main reports were issued.

- Due to setting a time reference for ages and in light of setting some indicators to a period of time reference too, this led to a confession for the survey management for age calculations, education, work and the malnutrition indicators. So to overcoming this issue in next sessions, it might help in approving the interview date to calculate the age and not be restricted to a time reference.

- Data on Education: education indicators were not published due to setting the age for time reference and this led to a gap between the field work in West Bank and in Gaza. In this context, the delays occurred in launching the fieldwork in the West Bank, led to collect data during summer vacation, causing confusion for field workers in collecting educational data; therefore, PCBS wasn’t able to publish them.

Seventh: The technical mission- New York

A technical mission was dispatched from UNICEF office in New York  to PCBS during 16/7/2012 -20/7/2012.

- The agenda and  objectives of the technical mission:

- Reviewing and evaluating the family survey data files 2010 at PCBS.

- The examination of the data files and its consistency and conformity with MICS4 standards.

- Preparing a final data file based on MICS4 standards and meeting PCBS criteria.

- Resolving all outstanding issues between PCBS and UNICEF in the details of Palestinian family survey 2010.

The following issues that were discussed with the mission on basis of its agenda and objectives:

- The issues that were addressed about data files at PCBS:

- A methodological problem related to defining targeted groups of women aged 15-45 years in the questionnaires of women health and awareness on AIDS. A bias was revealed in selecting of the qualified women to answer this part of questionnaire ( Weights were re-drawn and re0calculated , the results showed no important discrepancies)

- Age calculations and verifying time reference, according to standards, it was supposed to approve the interview date and not to assign a specific date as time reference because of its impact and bias in the selection, according to this principle, all the ages were calculated and it is expected to have an impact on the children files less than 5 years old and women health file as a result of the selection mechanism and age group.

- The youth selection methodology, especially in Jerusalem governorate, where it was agreed to keep the situation "as is" because Jerusalem (J1) has an exceptional situation in the sample.

- The general calculations of weights methodology: it was agreed to depend on the used methodology at PCBS.

- The conformity with MICS standards: most of the forms are, in general, identical with MICS4 standards and there is a need for some minor modifications for some variables due to the differences in the concept and the variable items.

- The set of the final report: UNICEF reviewed the files which haven’t been reviewed during the visit (elderly and youth); on the other hand, a final approved report from both UNIEF and PCBS has been obtained on 8/8/2012.

- The final report: it was agreed that the final report should be in accordance with the standards of MICS, while taken into account the Palestinian privacy, especially displaying those of additional indicators.

- The interview date on the family survey on the family questionnaire cover, to be reviewed and to modify the date to include the family interview date.

6.2 Recommendations

In light of the main survey with all phases, and the conclusions, one should recommend the following:

First: Recommendations regarding the project management

- Some issues should be agreed upon since the beginning of the survey and not on the time of launching the field work such as: survey title/ name, questionnaire design and  data entry program.

- UNICEF should conduct the workshop regarding data processing before launching any activity  so the survey management could be briefed on the partners requirements.

- Interview date shall be adopted when calculating the ages. A time reference will not be complied which will affect calculations of  malnutrition, age, education and work indicators.

- The survey is to be restricted to MICS standard questionnaire without any modules like the youth and the elderly questionnaires. This mainly aims at reducing the burden on field workers during training to better understanding the questions and giving more focus on training. This will also reduce the burden on families when collecting data so that they can give correct information. Additionally, it will help the families not get bored due to long questionnaires for better quality of the collected data.

- There were lots of details regarding terms of the signed agreement between PCBS and UNICEF without being enough discussed. There are still pending issues and details. Some of these details caused delays in publishing the survey outcomes. We recommend that agreement details should be taken into consideration and to review the possibility of implementing them before signing the agreement.

Second: Recommendations regarding field work

The big size of the questionnaire takes more than two hours to be answered by one family. PCBS recommend shortening the questionnaire into limited forms by excluding the youth and the elderly questionnaires.

Third: Recommendations regarding the information systems

The requirements of partners shall be adhered to  regarding data entry program and tests  to be uploaded on  before launching data processing.

Fourth: Recommendations regarding samples and sample frames

- The Palestinian family survey includes other categories other than that of UNICEF in MICS4 survey. These categories are the elderly and the youth which do not have dedicated forms for calculating weights (excel sheet) that was prepared by UNICEF. Therefore, it is significant to follow PCBS methodology in weights calculation.  There was a separate section for children aging from 2 to14 years where it needed a third stage to choose individuals. As a result, a dedicated weight was put for this category on a separate basis and this category is not included in the weight calculation form that was prepared by UNICEF. And thus, we recommend that MCIS4 to be dealt with on a standard basis which needs a standard design for MCIS survey separately.

- MICS survey sample shall be designed in the next time on separated basis other than annexes and modules (youth, elderly and others).

- The enumeration areas in the sample of next session (if implemented) shall be upgraded for the purpose of obtaining the right numbers and addresses of families before starting the survey. In the next session, data of census of 2007 are deemed old and they shall be upgraded.

Fifth: General recommendations

Many problems and obstacles could have been avoided through reviewing the possibility of postponing the survey implementation until the beginning of 2011.

Sixth: Recommendations of the technical mission (UNICEF)

- Age calculations in the upcoming surveys shall be done on basis of on the interview date and not based on the attribution date as done in the Palestinian family survey in 2010.

- The questionnaire size shall be taken into consideration when designing the upcoming survey questionnaires.

- The added questions to the survey up on requests of partners should be reviewed and its uses.

- Two separate questionnaires for women who have been married and women who have not been married should not be used. They should be replaced by using skips as needed (in future surveys).

- Data entry programs and attached standard programs should be used due to  benefits of limiting and avoiding data entry errors.